## Sayfa1
Risk No | Risk Description | Likelihood (1–5) | Impact (1–5) | Risk Level | Mitigation Strategy
1 | Insufficient amount of Turkish joke data | 4 | 4 | 16 | Apply data augmentation techniques; expand the dataset using similar humor sources
2 | Limited weekly time availability of team members (6–8 hours) | 4 | 3 | 12 | Use Trello for task tracking; set realistic sprint goals based on availability
3 | Low model performance (BLEU score or human evaluation) | 3 | 4 | 12 | Start with simple baseline models and iteratively improve; adjust hyperparameters and try alternative architectures
4 | Generation of unethical or culturally inappropriate jokes | 3 | 5 | 15 | Implement human-in-the-loop validation; add filtering layers and enforce content guidelines
5 | Computing resource limitations on platforms like Google Colab | 3 | 3 | 9 | Split training sessions into smaller batches; explore alternatives like Hugging Face Spaces or Kaggle Kernels
6 | Large Language Model (LLM) usage may exceed available hardware | 2 | 4 | 8 | Prefer lightweight architectures (e.g., GRU, LSTM); only use LLMs for minimal fine-tuning when feasible